## Functional - Mehedi
Tracking ID | Module/Sub Module/Feature | Build Version/URL | Testing Date | Issue Findings (Issue name, Steps to reproduce, Actual Result, Expected Result, Test Data) | Issue Category | Issue Type | Priority | QA Status | QA Name | QA Remarks | Attachment | Reporting Manager's Feedback | Current Iteration | Issue Occurance Count | Developer Name | Issue Status-Developers Feedback | Developer's Remark | Defect Solved Date
TC_001 | Login |  | 2023-02-02 | Validation is missning for empty credential | Bugs | Functionality Errors | High | Open | Ridwan | [5 empty] | Amirul Islam | Solved
TC_002 | Login |  | 2023-02-02 | Validation message missing for empty/invalid credential | Bugs | Functionality Errors | High | Open | Ridwan | [5 empty] | Amirul Islam | Solved
TC_003 | Login |  | 2023-02-02 | Remember me functionality is not working | Bugs | Functionality Errors | High | Open | Ridwan
TC_004 | Create Flow > Add question |  | 2023-02-02 | No validation is set for empty value in add question form and its showing page error when to submit with empty value | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_005 | Create Flow > Add question |  | 2023-02-02 | Validation message is not showing properly for empty value | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_006 | Create Flow > Add question |  | 2023-02-02 | No input box is showing for input type question | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_007 | Create Flow > Add question |  | 2023-02-02 | When submit any question keeping multiple choice box empty, showing 505 error | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_008 | Create Flow > Edit question |  | 2023-02-02 | When edit a question multiple choice to input box, after updating its showing as multiple choice question | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_009 | Create Flow > Edit question |  | 2023-02-02 | When edit a question input box to multiple choice question, it's showing 505 error | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_010 | Create Flow > Edit question |  | 2023-02-02 | When edit question, missing validation in Select Ans type filed, it accepts empty selection | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_011 | Create Flow |  | 2023-02-02 | Question numbering is showing twice | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_012 | Create Flow |  | 2023-02-02 | When click to add question and fillup the fields and close the tab, it stores the data and display in the fileds when again click to add question | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_013 | Create Flow |  | 2023-02-02 | During editing/creaing description, when click to outside of the text box, editing is being discard | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Not Solved
TC_014 | Create Flow |  | 2023-02-02 | No character limit is set for project name, question title, description and quiz option | Bugs | Functionality Errors | High | Open | Ridwan | [5 empty] | Eamin | Solved |  | 2023-02-06
TC_015 | Create Flow |  | 2023-02-02 | Description field is not considered as mendatory field | Bugs | Functionality Errors | High | Open | Ridwan | [5 empty] | Eamin | Solved | Description field is nullable | 2023-02-06
TC_016 | Edit flow |  | 2023-02-02 | Name formate changes when edit flow | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_017 | Flow list > Delete flow |  | 2023-02-02 | Couldn't able to delete flow when question is added | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_018 | Flow list > Delete flow |  | 2023-02-02 | Alert message text is showing twice when try to delete flow | Bugs | Functionality Errors | High | Open | Ridwan | [5 empty] | Eamin | Solved | When flow have any question, then ask for confirmation twice. | 2023-02-06
TC_019 | Flow list |  | 2023-02-02 | Submitted time is showing wrong | Bugs | Functionality Errors | High | Open | Ridwan | [5 empty] | Eamin | Solved | All time shown in GMT+0 | 2023-02-06
TC_020 | IoGT > File list |  | 2023-02-02 | Time is showing wrong | Bugs | Functionality Errors | High | Open | Ridwan | [5 empty] | Eamin | Solved |  | 2023-02-06
TC_021 | IoGT > File list |  | 2023-02-02 | Searching is not working | Bugs | Functionality Errors | High | Open | Ridwan | [5 empty] | Eamin | Solved |  | 2023-02-06
TC_022 | IoGT > File list |  | 2023-02-02 | View, edit and delete button is not working | Bugs | Functionality Errors | High | Open | Ridwan
TC_023 | IoGT > File list |  | 2023-02-02 | Scroll issue when click for any action view/edit/delete | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_024 | IoGT > File list |  | 2023-02-02 | Push to IoGT is not working | Bugs | Functionality Errors | High | Open | Ridwan
TC_025 | IoGT > File list |  | 2023-02-02 | Pagination missing | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_026 | IoGT > Translate Files |  | 2023-02-02 | Choose file functionality is not working | Bugs | Functionality Errors | High | Open | Ridwan
TC_027 | IoGT > Translate file |  | 2023-02-05 | Successful popup is missing after saving translate file | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_028 | IoGT > Translate file |  | 2023-02-05 | Select language is being empty | Bugs | Functionality Errors | High | Open | Ridwan
TC_029 | Admin > Admin create |  | 2023-02-05 | Validation is message is not set for country field | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_030 | Admin > Admin create |  | 2023-02-05 | Minimum character/number/digit validation is missing for password | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_031 | Admin > Admin create |  | 2023-02-05 | After creating new admin, sometimes show no record found | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_032 | Admin > Edit admin |  | 2023-02-05 | When perform any action/edit in page 2, after completing it redirects user to page 1. should stay in current page | Bugs | Functionality Errors | High | Open | Ridwan
TC_033 | Admin > Edit admin |  | 2023-02-05 | Country field validation missing when edit admin details | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_034 | Editor > Add Editor |  | 2023-02-05 | No validation is set for platform field, accept empty user input | Bugs | Functionality Errors | High | Open | Ridwan | [5 empty] | Eamin | Solved |  | 2023-02-06
TC_035 | Editor > Edit Editor |  | 2023-02-05 | Validation is not set for all the fields when edit editor information, validation message is not showing | Bugs | Functionality Errors | High | Open | Ridwan
TC_036 | Editor > Edit Editor |  | 2023-02-05 | Field are being blank when to edit editor information | Bugs | Functionality Errors | High | Open | Ridwan
TC_037 | Editor > Edit Editor |  | 2023-02-05 | When edit editor information, doesn't display country for region | Bugs | Functionality Errors | High | Open | Ridwan
TC_038 | Editor |  | 2023-02-05 | Editor platform access is not working for editor side, only showing settings from editor side (dependency) | Bugs | Functionality Errors | High | Open | Ridwan | [5 empty] | Eamin |  |  | 2023-02-06
TC_039 | Editor |  | 2023-02-05 | User login session will automatic get logout when his status will be changed active to inactive by super admin | Bugs | Functionality Errors | High | Open | Ridwan
TC_040 | Editor |  | 2023-02-05 | Should not be able to login when editor status is inactive | Bugs | Functionality Errors | High | Open | Ridwan | [5 empty] | Eamin | Solved |  | 2023-02-06
TC_041 | Editor |  | 2023-02-05 | Pagination missing | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_042 | Profile |  | 2023-02-05 | Should display size limit alert and file type alert before updating | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_043 | Profile |  | 2023-02-05 | Name and email field validation should set from frontend, Should not be able perform update with empty credential | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_044 | Profile |  | 2023-02-05 | Confirmation pop up missing before logout | Bugs | Functionality Errors | High | Open | Ridwan
TC_045 | Profile > Password changing |  | 2023-02-05 | Old password and new password should not be the same | Bugs | Functionality Errors | High | Open | Ridwan
TC_046 | Password |  | 2023-02-05 | All the password filed should have a minimum character/digit requirement | Bugs | Functionality Errors | High | Open | Ridwan
TC_047 | Notification |  | 2023-02-05 | Notification functionality is not working | Bugs | Functionality Errors | High | Open | Ridwan
TC_048 | Profile name |  | 2023-02-05 | Clicking to name in right top bar doesn't perform any action | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_049 | File Report > Region |  | 2023-02-06 | Thematic area count is not being updated | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_050 | File Report > Region > View region |  | 2023-02-06 | Pagination missing | Bugs | Functionality Errors | High | Open | Ridwan
TC_051 | File Report > Rapid pro |  | 2023-02-06 | FIlter button is not working | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_052 | File Report > Rapid pro |  | 2023-02-06 | Action field is empty | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_053 | File Report > Rapid pro |  | 2023-02-06 | Time is showing wrong | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_054 | File Report > Rapid pro |  | 2023-02-06 | Searching isn't working for all the columns | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_055 | File Report > IoGT |  | 2023-02-06 | No data is found | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_056 | File Report > IoGT |  | 2023-02-06 | Pagination missing | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_057 | Dashboard |  | 2023-02-06 | Push to rapid pro and Frequency of Rapidpro Push value is not correct | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_058 | Dashboard |  | 2023-02-06 | User summary value is not correct | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_059 | Dashboard |  | 2023-02-06 | Regional admin count is showing wrong | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_060 | Dashboard |  | 2023-02-06 | IoGT Push count is showing wrong | Bugs | Functionality Errors | High | Open | Ridwan | [6 empty] | Solved
TC_061 | Create flow |  | 2023-03-14 | Validation missing for empty value in option of multiple choice question | Bugs | Functionality Errors | High | Open | Ridwan
TC_062 | Create flow |  | 2023-03-14 | Response message is not showing when answer type is input box | Bugs | Functionality Errors | High | Open | Ridwan
TC_063 | Create flow |  | 2023-03-14 | When any sub question is input box its being skipped after selecting option in response for that question | Bugs | Functionality Errors | High | Open | Ridwan
TC_064 | Create flow |  | 2023-03-14 | Add sub question option is showing though the previous subquestion is type of inputbox | Bugs | Functionality Errors | High | Open | Ridwan
TC_065 | Create flow |  | 2023-03-15 | Couldn't add questions when the question type is multiple choice and tried to add 8 options. After adding 8 options and clicking to add, showing the question was created successfully but there is no question displaying, also couldn't delete that flow when trying to delete, showing the question is added already. Couldn't add questions further in this flow. | Bugs | Functionality Errors | High | Open | Ridwan
TC_066 | Create flow |  | 2023-03-15 | Character limit missing for Add response field and option field | Bugs | Functionality Errors | High | Open | Ridwan
TC_067 | Create flow |  | 2023-03-15 | Wrong subquestion appears after selecting answer | Bugs | Functionality Errors | High | Open | Ridwan
TC_068 | Create flow |  | 2023-03-15 | Question edit button missing | Bugs | Functionality Errors | High | Open | Ridwan
TC_069 | Create flow |  | 2023-03-15 | Should be able to add multiple subquestion in response of one option | Bugs | Functionality Errors | High | Open | Ridwan
TC_070 | Left dropdown |  | 2023-03-15 | Animation flickering issue | Bugs | Functionality Errors | High | Open | Ridwan